## Project Budget
Project Budget Template
Project Name: | Cyber Security Risks Research Project
Department: | IT
Supervisor Name: | Ryan Wickramaratne
|  | Materials | [5 empty] | BALANCE
|  | Unit Price | Units | Travel | Other | BUDGETED | ACTUAL | UNDER/OVER
WBS | Project Tasks
1.1 | Requirements gathering and analysis | [6 empty] | 0
| Books and Documents | 500 | 5 | 1000 | 0 | 2000 | 3500 | -1500
| Communication Process |  |  | 5000 | 5000 | 1000 | 10000
| Analysis software cost | 1 | 2000 | 0 | 0 | 0 | 2000 | -2000
1.2 | Project charter development | [5 empty] | 0 | 0
| Document process | 0 | 0 | 0 | 0 | 2000 | 0 | 2000
[7 empty] | 0 | 0
2.1 | Project plan development | [5 empty] | 0 | 0
| Document process | 0 | 0 | 0 | 0 | 2000 | 0 | 2000
| Software costs | 4000 | 1 | 0 | 0 | 2000 | 4000 | -2000
[7 empty] | 0 | 0
3.1 | Data Collection | [5 empty] | 0 | 0
| Collecting data through internet |  |  |  | 2000 | 5000 | 2000 | 3000
| Collecting data through people | 0 | 0 | 4000 | 2000 | 2000 | 6000 | -4000
| Telephone cost | 0 | 0 | 0 | 2000 | 3000 | 2000 | 1000
3.2 | Data Analyzation | [5 empty] | 0 | 0
| Document Process | 0 | 0 | 0 | 0 | 2000 | 0 | 2000
| Analyzing process | 0 | 0 | 0 | 4000 | 6000 | 4000 | 2000
[7 empty] | 0 | 0
4.1 | Data Collection | [5 empty] | 0 | 0
| Document Process | 0 | 0 | 0 | 0 | 2000 | 0 | 2000
| Software costs | 1000 | 2 | 600 | 1000 | 0 | 3600 | -3600
0
| SUBTOTAL |  |  | 10600 |  | 29000 | 37100 | -8100

## How to Use this Template
Introduction
Use this project budget template to track all of your project expenses at a task level. Simply enter data into the fields, and your over/under will be automatically calculated. Remember, a successful project is one that comes in under budget.
Definition of Terms
WBS: Work breakdown structure lets you see the hierarchy of tasks as a number
Task: Enter the name of the task being worked on.
Assigned To: Who is responsible for the task
Planned HR: Enter the number of hours you expect the task to take.
Actual HR: Enter the number of billable hours the work actuallty took.
Labor $/HR: Enter how much money per hour that labor cost you.
Materials UNITS: Enter how many units of material you needed to complete the task.
Materials $/UNITS: Enter how much money each unit cost.
Travel: Enter the total travel expenses.
EQUP/SPACE: Enter how much your equipment or office space costs.
FIXED: Enter any costs that are fixed and unchanging.
MISC: Enter any other known costs.
BUDGET: Enter your budget for the task.
ACTUAL: This field will be automatically calculated based on the other costs entered in the row.
UNDER/OVER: This will be automatically calculated based on the budget vs actual fields.
SUBTOTAL: This row sums all the rows above it to give you a subtotal for the project.